## High-level outline.
Execution plan into actionable steps:
Phase 1: Commodity Selection & Market Research (Weeks 1-4)
1. Identify a commodity:
- Choose a raw material with high demand and growth potential (e.g., cashew, cocoa, sesame)
- Assess production volumes, quality, and competition in Africa
2. Market research:
- Analyze global market trends, prices, and demand forecasts
- Identify potential buyers, competitors, and partners
- Evaluate regulatory frameworks and trade agreements
Phase 2: Country & Partner Selection (Weeks 5-8)
1. Country selection:
- Evaluate production capacity, infrastructure, and business environment
- Choose a country with a stable government, favorable policies, and abundant raw materials (e.g., Côte d'Ivoire, Ghana, Ethiopia)
2. Partner identification:
- Find local farmers, cooperatives, or processors interested in value-addition partnerships
- Identify technical partners (e.g., equipment suppliers, agronomists)
- Connect with potential investors, DFIs, or foundations
Phase 3: Business Model & Investment Thesis (Weeks 9-12)
1. Develop a business model:
- Define the value-addition process (e.g., local roasting, oil extraction)
- Create a revenue model (e.g., deal fees, equity carry, minority stakes)
- Outline operational structure and partnerships
2. Refine the investment thesis:
- Highlight supply security, processing upgrades, and market access
- Define target returns (IRR 15-25%) and exit strategies
Phase 4: Capital Raising & Structuring (Weeks 13-20)
1. Develop a capital stack:
- Approach DFIs, foundations, and local banks for funding
- Attract private equity or family offices for growth equity
- Engage strategic buyers for offtake agreements and minority stakes
2. Structure the deal:
- Create a special purpose vehicle (SPV) or joint venture
- Negotiate terms with partners and investors
Phase 5: Implementation & Operations (After Week 20)
1. Set up local operations:
- Establish a local office and team
- Procure equipment and technology
- Train staff and partners
2. Source raw materials:
- Contract farmers or cooperatives
- Implement quality control and logistics
3. Process and sell:
- Start processing and value-addition activities
- Sell products to regional or export markets
Key Performance Indicators (KPIs)
- Commodity prices and market trends
- Production volumes and quality
- Revenue growth and profitability
- Partnerships and collaborations
- Investor returns and exit opportunities

## Phase 1
Phase 1: Commodity Selection & Market Research (Weeks 1-4)
1. Commodity Identification:
- Research top African export commodities (e.g., cocoa, cashew, coffee, cotton, sesame)
- Evaluate factors:
- Global demand growth
- Price trends and volatility
- Production volumes in Africa
- Competition and market saturation
- Shortlist 2-3 commodities
2. Market Research:
- Analyze global market trends and forecasts
- Identify key players:
- Buyers (importers, traders, manufacturers)
- Competitors (other African exporters, global suppliers)
- Potential partners (processors, traders)
- Assess regulatory frameworks:
- Trade agreements (e.g., AfCFTA, EU-EAFTA)
- Tariffs, duties, and taxes
- Quality and safety standards
3. Value Chain Analysis:
- Map the commodity value chain:
- Production → processing → trading → manufacturing → consumption
- Identify bottlenecks and opportunities for value addition
4. Feasibility Assessment:
- Evaluate the potential for value addition in Africa:
- Processing costs and feasibility
- Market access and demand
- Competition and barriers to entry
Output: A shortlist of 1-2 commodities with high potential for value addition in Africa, along with a market research report.

## Phase 2
Phase 2: Country & Partner Selection (Weeks 5-8)
1. Country Selection:
- Evaluate African countries with significant production of the chosen commodity:
- Production volumes and growth potential
- Infrastructure (ports, roads, energy)
- Business environment and regulatory framework
- Political stability and security
- Shortlist 2-3 countries
2. Country Deep Dive:
- Assess the commodity-specific ecosystem:
- Farmer organizations and cooperatives
- Existing processors and manufacturers
- Government policies and incentives
- Evaluate infrastructure:
- Logistics and transportation costs
- Energy costs and reliability
- Access to finance and banking
3. Partner Identification:
- Identify potential local partners:
- Farmers or cooperatives
- Processors or manufacturers
- Technical partners (e.g., equipment suppliers)
- Evaluate partner capabilities and fit:
- Production capacity and quality
- Market access and networks
- Financial stability and credibility
4. Partner Engagement:
- Initial outreach and meetings:
- Discuss potential partnership opportunities
- Assess interest and commitment
- Share vision and expectations
Output: A shortlisted country and potential local partners for the chosen commodity, along with a partnership framework.

## Phase 3
Phase 3: Business Model & Investment Thesis (Weeks 9-12)
- Commodity: [Chosen commodity] (e.g., cocoa, coffee, cashew)
- Country: [Chosen country] (e.g., Ghana, Ethiopia, Côte d'Ivoire)
Business Model:
- Value proposition: Provide local processing and value addition services to [country]'s [commodity] farmers and cooperatives, increasing their revenue.
- Product/service: Offer [value-added product/service] (e.g., roasting, grinding, processing) for local and export markets.
- Target market:
- Local [industry/manufacturers]
- Export markets (e.g., EU, US, Asia)
- Revenue streams:
- Processing fees
- Sales of value-added products
- Potential equity stakes or partnerships
- Key partners:
- Local farmers and cooperatives
- Technical partners (e.g., equipment suppliers)
- Potential investors or buyers
Investment Thesis:
- Supply security: Access [commodity] from [country]'s farmers
- Processing upgrade: Improve quality and add value with modern processing
- Market access: Tap into [market/industry] demand
- Returns: Target IRR 15-25% through processing fees and sales
- Exit path: Potential sale, partnership, or listing

## Phase 4
Phase 4: Capital Raising & Structuring (Weeks 13-20)
Capital requirements: Estimate funding needs for:
- Processing facility setup (CAPEX)
- Working capital (e.g., raw material sourcing, operational costs)
- Marketing and sales efforts
Capital stack:
- DFIs/foundations: First-loss or concessional funding
- Local banks: Working capital or debt financing
- Private equity/family offices: Growth equity
- Strategic buyers: Offtake agreements or minority stakes
Investor targeting:
- Identify potential investors aligned with the project
- Prepare pitch materials (e.g., investment memo, financial projections)
- Engage investors and negotiate terms
Structuring:
- Set up SPV (Special Purpose Vehicle) or joint venture
- Define equity and debt structures
- Align interests of partners and investors
Key activities:
- Prepare financial projections and business case
- Engage with potential investors and partners
- Negotiate terms and structure deal
Capital Structuring:
- Equity: Founders' equity, investor equity (e.g., private equity, strategic investors)
- Debt: Local bank loans, DFI loans, or concessional funding
- Grants or incentives: Government grants, DFI grants, or tax incentives
- Offtake agreements: Secure offtake agreements with buyers to reduce risk and secure funding
Example Capital Structure:
- Equity: 30% (founders, investors)
- Debt: 50% (local bank, DFI loan)
- Grants/incentives: 10% (government grant for processing facility)
- Offtake agreements: 10% (value of secured offtake agreements)
Key considerations:
- Risk allocation: Allocate risks to parties best equipped to manage them
- Governance: Define decision-making rights and board representation
- Exit: Define exit options and potential returns for investors
- Currency risk: Manage FX risk if dealing with multiple currencies

## Phase 5
Phase 5: Implementation & Operations
Setup local operations:
- Establish a local office and team
- Procure equipment and technology
- Train staff and partners
Source raw materials:
- Contract farmers or cooperatives
- Implement quality control and logistics
Process and sell:
- Start processing and value-addition activities
- Sell products to regional or export markets
Monitor and optimize:
- Track KPIs (e.g., production costs, quality, sales)
- Optimize operations for efficiency and profitability
Key focus areas:
- Ensure smooth operations and production
- Build relationships with suppliers and buyers
- Manage risks and challenges
- Drive growth and scalability
List of potential stakeholders and their deliverables/responsibilities
Stakeholders and Responsibilities
1. Project Sponsors/Investors
- Deliverables: Provide funding, strategic guidance
- Responsibilities: Approve project plans, ensure funding disbursement
2. Local Farmers/Cooperatives
- Deliverables: Supply quality raw materials (cocoa, coffee beans)
- Responsibilities: Maintain quality standards, deliver on quantity commitments
3. Project Management Team
- Deliverables: Project implementation, operations, reporting
- Responsibilities: Manage day-to-day operations, meet project goals
4. Technical Partners (e.g., equipment suppliers)
- Deliverables: Provide equipment, training, maintenance
- Responsibilities: Ensure equipment functionality, support operations
5. Local Government/Regulators
- Deliverables: Permits, approvals, regulatory compliance
- Responsibilities: Ensure project complies with local laws/regulations
6. Buyers/Offtakers
- Deliverables: Purchase agreements, timely payments
- Responsibilities: Offtake products, meet quality/quantity requirements
7. Financial Institutions/Banks
- Deliverables: Financing, financial services
- Responsibilities: Disburse funds, manage financial transactions
8. Logistics/Transport Partners
- Deliverables: Timely delivery of inputs/outputs
- Responsibilities: Manage logistics, ensure product quality
9. Local Community/NGOs
- Deliverables: Support for project sustainability, community engagement
- Responsibilities: Engage with community, support project goals
10. Employees/Staff
- Deliverables: Operational tasks, performance targets
- Responsibilities: Execute tasks, contribute to project success
11. Customers/End-users
- Deliverables: Feedback, repeat business
- Responsibilities: Provide feedback, purchase products
12. Suppliers/Input Providers
- Deliverables: Quality inputs (e.g., seeds, fertilizers)
- Responsibilities: Supply inputs on time, ensure quality
13. Insurance Providers
- Deliverables: Risk coverage, claims processing
- Responsibilities: Provide insurance coverage, process claims
14. Auditors/Accountants
- Deliverables: Financial reports, compliance
- Responsibilities: Ensure financial accuracy, compliance with standards
15. Legal Advisors
- Deliverables: Legal compliance, contracts
- Responsibilities: Advise on legal matters, draft contracts
16. Environmental/Sustainability Assessors
- Deliverables: Environmental impact assessments
- Responsibilities: Ensure project meets environmental standards